## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Sales forecasting product (prototype) |  |  |  |  | COMPANY NAME
PROJECT MANAGER |  | Leo |  |  |  |  | DATE | [6 empty] | 2022-05-15
[7 empty] | Starting 15-May | [39 empty] | Deadline 15-Jul
| TASK TITLE | TASK OWNER | START DATE | DUE DATE | Days | PCT OF TASK COMPLETE | Concepting | [14 empty] | Developing | [19 empty] | Performance | [9 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Domain analysis | Leo Ma | 2022-05-16 | 2022-05-18 | 3 | 0% | bar: WEEK 1 M to WEEK 1 W
1.2 | Product aim direction | Leo Ma | 2022-05-19 | 2022-05-23 | 3 | 0% | bar: WEEK 1 R to WEEK 2 M
1.3 | Research | Leo Ma | 2022-05-24 | 2022-06-01 | 7 | 0% | bar: WEEK 2 T to WEEK 3 W
1.4 | Developing planing | Leo Ma | 2022-06-02 | 2022-06-03 | 2 | 0% | bar: WEEK 3 R to WEEK 3 F
2 | Product development
2.1 | coding (1st group model) + Test | Leo Ma | 2022-06-06 | 2022-06-09 | 3 | 0% | bar: WEEK 4 M to WEEK 4 R
2.2 | coding (2nd group model)+ Test | Leo Ma | 2022-06-10 | 2022-06-15 | 3 | 0% | bar: WEEK 4 F to WEEK 5 W
2.3 | coding (3rd group model)+ Test | Leo Ma | 2022-06-16 | 2022-06-21 | 3 | 0% | bar: WEEK 5 R to WEEK 6 T
2.4 | coding (data output) + final test | Leo Ma | 2022-06-22 | 2022-06-24 | 3 | 0% | bar: WEEK 6 W to WEEK 6 F
2.5 | output visualization design | Leo Ma | 2022-06-27 | 2022-07-01 | 5 | 0% | bar: WEEK 7 M to WEEK 7 F
3 | Project Performance
4.1 | Product output review | Leo Ma | 2022-07-04 | 2022-07-04 | 1 | 0% | bar: WEEK 8 M
4.2 | User beta test | Leo Ma | 2022-07-05 | 2022-07-06 | 2 | 0% | bar: WEEK 8 T to WEEK 8 W
4.3 | Improvement base beta test | Leo Ma | 2022-07-07 | 2022-07-08 | 2 | 0% | bar: WEEK 8 R to WEEK 8 F
4.4 | Project report | Leo Ma | 2022-07-11 | 2022-07-15 | 5 | 0% | bar: WEEK 9 M to WEEK 9 F

## Sheet1
Project am: |  | Forecasting sales
Multi-Layer Perceptron (MLP)
Bayesian Neural Network (BNN)
Radial Basis Functions (RBF)
Generalized Regression Neural Networks (GRNN), also called kernel regression
K-Nearest Neighbor regression (KNN)
CART regression trees (CART)
Support Vector Regression (SVR)
Gaussian Processes (GP)
Modern :
Recurrent Neural Network (RNN)
Long Short-Term Memory (LSTM)
Linear regression
Random Forest regression
XGBoost